## Biomag - Activities
Sl.No. | Activities | Owner | Pl.Date | Act.Date | Status | Notes
1 | Review release plan with Dr.Garcia | Dr.Garcia and Bandita | 2017-04-24 |  | Open
2 | Release readiness / pre-requisites (List of items to initiate at the beginning) |  |  |  | Open
2.1 | New AWS Account for Production Release | Dr.Garcia and Bandita | 2017-04-25 |  | Open
2.2 | Master Data Accuracy | Dr.Garcia and Bandita | 2017-04-26 |  | Open
2.3 | 3D Plotted Points Accuracy | Dr.Garcia and Bandita | 2017-04-26 |  | Open
2.4 | Product Demo/Training Video | Dr.Garcia and Bandita | 2017-04-27 |  | Open
2.5 | Bank Account for Product Transactions | Vmoksha | 2017-05-05 |  | Open
3 | Observe the Therapy Process followed, find new features to include for Subsequent Phases of the Apps release | Bandita | 2017-04-24 |  | Open | Daily Task.
4 | Finalize New 3D Models with option of hiding and displaying Internal organs | Dr.Garcia and Bandita | 2017-04-28 |  | Open
5 | Requirement Analysis |  |  |  | Open
5.1 | New Mobile App for Biomagnetism Learning Courses | Dr.Garcia and Bandita | 2017-05-01 |  | Open | 2 day work
5.2 | Emotional Pairs, Pregnancy Pairs, Chakras, etc. | Dr.Garcia and Bandita | 2017-05-03 |  | Open
5.3 | Functional Requirements for Implementation of 3D Models with Internal Organs display | Dr.Garcia and Bandita | 2017-05-04 |  | Open
5.4 | Radio-active Therapy using Biomagnetism | Dr.Garcia and Bandita | 2017-05-05
5.5 | Collect information and understanding on latest Therapy Developments in Biomagnetism to include as New Feature | Dr.Garcia and Bandita | 2017-04-24 |  | Open | On-going process.
6 | End to end application dry run with Dr.Garcia (from the deployed version of Biomag Practitioner App, Biomag 3D, Master Data Management Web, Practitioner (Web), Brochure) | Dr.Garcia and Bandita | 2017-04-24 |  | Open | On-going process.
7 | User Guide & App Guidelines | Dr.Garcia and Bandita | 2017-05-03 |  | Open
8 | Miscellaneous (Outside the project and if time permits) | Dr.Garcia and Bandita |  |  | Open | Whenever possible
8.1 | Meeting & get introduced with other Staff and Practitioners | Dr.Garcia and Bandita |  |  | Open
9 | Daily review & Status Update | Dr.Garcia and Bandita |  |  | Open
9.1 | Between Dr.Garcia & Vmoksha Onsite (Morning EDT) | Dr.Garcia and Bandita | 2017-04-24 |  | Open
9.2 | Between Vmoksha Onsite & Offshore (Evening EDT) | Dr.Garcia and Bandita | 2017-04-24 |  | Open
10 | Analyze Next Phase CRs | Dr.Garcia and Bandita | 2017-05-04 |  | Open
11 | Interact with visited Client and accumulate a list of Pain-Points and Suggestions for Improvement | Dr.Garcia and Bandita | 2017-04-24 |  | Open | On-going process.

## Queries
Sl.No. | Query Description | Document Name | Screen Spec Id | Raised By | Raised Date | Response Description | Response Sent By | Response Received Date | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Client Reported Issues
Sl.No | Github # | Type | User | Issue | Root Cause
1
2
3
4
5
6
7
8

## Next Phase CRs List
Sl.No. | Github Ticket | Description | Estimated Effort | Phase | Status | Comments
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
Total |  |  | 0