## Biomag - Activities
Sl.No. | Activities | Owner | Planned Date | Actual Date | Status | Notes
1 | Review release plan with Dr. Garcia | Dr. Garcia & Bandita | 2017-04-24 |  | Open
2 | Release readiness / pre-requisites (List of items to initiate at the beginning) |  |  |  | Open
2.1 | New AWS Account for Production Release | Dr. Garcia & Bandita | 2017-04-25 |  | Open
2.2 | Master Data Accuracy | Dr. Garcia & Bandita | 2017-04-26 |  | Open
2.3 | 3D Plotted Points Accuracy | Dr. Garcia & Bandita | 2017-04-26 |  | Open
2.4 | Product Demo/Training Video | Dr. Garcia & Bandita | 2017-04-27 |  | Open
2.5 | Bank Account for Product Transactions | Vmoksha | 2017-05-05 |  | Open
3 | Observe the Therapy Process followed, find new features to include for Subsequent Phases of the Apps release | Bandita | 2017-04-24 |  | Open | Daily Task.
4 | Finalize New 3D Models with option of hiding and displaying Internal organs | Dr. Garcia & Bandita | 2017-04-28 |  | Open
5 | Requirement Analysis |  |  |  | Open
5.1 | New Mobile App for Biomagnetism Learning Courses | Dr. Garcia & Bandita | 2017-05-01 |  | Open | 4 day work
5.2 | Emotional Pairs, Pregnancy Pairs, Chakras, etc. | Dr. Garcia & Bandita | 2017-05-03 |  | Open
5.3 | Functional Requirements for Implementation of 3D Models with Internal Organs display | Dr. Garcia & Bandita | 2017-05-04 |  | Open
5.4 | Radio-active Therapy using Biomagnetism | Dr. Garcia & Bandita | 2017-05-05 |  | Open
5.5 | Collect information and understanding on latest Therapy Developments in Biomagnetism to include as New Feature | Dr. Garcia & Bandita | 2017-04-24 |  | Open | On-going process.
6 | End to end application dry run with Dr.Garcia (from the deployed version of Biomag Practitioner App, Biomag 3D, Master Data Management Web, Practitioner (Web), Brochure) | Dr. Garcia & Bandita | 2017-04-24 |  | Open | On-going process.
7 | User Guide & App Guidelines | Dr. Garcia & Bandita | 2017-05-03 |  | Open
8 | Miscellaneous (Outside the project and if time permits) | Dr. Garcia & Bandita |  |  | Open | Whenever possible
8.1 | Meeting & get introduced with other Staff and Practitioners | Dr. Garcia & Bandita |  |  | Open
9 | Daily review & Status Update | Dr. Garcia & Bandita |  |  | Open
9.1 | Between Dr. Garcia & Vmoksha Onsite (Morning EDT) | Dr. Garcia & Bandita | 2017-04-24 |  | Open
9.2 | Between Vmoksha Onsite & Offshore (Evening EDT) | Dr. Garcia & Bandita | 2017-04-24 |  | Open
10 | Analyze Next Phase CRs | Dr. Garcia & Bandita | 2017-05-04 |  | Open
11 | Interact with visited Client and accumulate a list of Pain-Points and Suggestions for Improvement | Dr. Garcia & Bandita | 2017-04-24 |  | Open | On-going process.
12 | Biomag 3D Desktop Application inputs / discussion | Dr. Garcia & Bandita |  |  | Open
13 | Discussing & Finalizing Logo for Beyond BioMag brand | Dr. Garcia & Bandita |  |  | Open
14 | Client Data migration / entry (Production Data) | Dr. Garcia & Bandita |  |  | Open
15 | Spanish Data collection | Dr. Garcia & Bandita |  |  | Open
16 | Data capturing for Advance version | Dr. Garcia & Bandita |  |  | Open

## Senthil Inputs
ACTIVITY | REMARKS
Onsite Visit Itinerary
App - Beta Testing & Training to Stakeholders
Beyond BioMag - 3D App
Beyond BioMag - Practioner App
Beyond BioMag - Web App
Beyond BioMag - API
Product Launch @ <Venue name> | Dr. has to provide the address and make things ready
New features - requirement gathering
Design & strategize the digitization of hard copies of practioner app into the system
Work with Jeannett to prepare a professional 2 minutes app video
Readiness
Beyond Biomag Logo
Launch event invitation - content & design
Promotional website - Release it to production with DNS www.beyondbiomag.io
Practioner website - practioner.beyondbiomag.io
Ipad app with API's pointing to api.beyondbiomag.io
Setup monitoring tool for API end points, Web application
Setup maintenance team for Beyond Biomag
Prepare brochures, Letter heads, Business card design, any stickers
T-shirt for Beyond Biomag | This can be taken up with lower priority
Video shoot to talk about Beyond BioMag which will be played during launch event
Technical Items
Beyond Biomag 3D Notification email
Sign-up welcome email - html formatted, nice looking in biomag brand and colr theme
Forgot Password - html formatted, nice looking in biomag brand and colr theme
DB Backup is setup and stored in S3
Enable Load balancer
Enable https for web & rest api
Full roll-out to apple store including complete payment
Make sure the money gets credited to the account
Test apple account emails used for developer account, subscription etc.
IS should setup cloud monitoring tool to monitor api end points, web application are working. Notify users during any breaks
Create a dedicated new Github account using beyondbiomag email id
Create email accounts using beyondbiomag domain
hello@beyondbiomag.io
support@beyondbiomag.io
alert@beyondbiomag.io
admin@beyondbiomag.io
Push notification - Any subscription | Speak to bhuvan how we can send puch notification from web panel using our existing code base
Short video tutorial about (Using the real screen play)
Beyond BioMag - 3D App
Beyond BioMag - Practioner App
Beyond BioMag - Web App
Promotional Website
General Features
Contact us - Email should land @ hello@beyondbiomag.com
Terms & Conditions
Privacy Policy
Contact Us
Social media links
Faq
Videos

## Next Phase CRs List (hidden)
Sl.No. | Github Ticket | Description | Estimated Effort | Phase | Status | Comments
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
Total |  |  | 0

## Client Reported Issues (hidden)
Sl.No | Github # | Type | User | Issue | Root Cause
1
2
3
4
5
6
7
8

## Queries (hidden)
Sl. No. | Query Description | Document Name | Screen Spec Id | Raised By | Raised Date | Response Description | Response Sent By | Response Received Date | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30